# APHL 75th Anniversary Timeline

NOW

- Create and order clings/signage for office - BM

- Order giveaways (office visitors, AC and PHLAM distribution): are stickers or pins worth it as a little giveaway throughout the year? (Flat Labby stress “ball”) – BM/TM

- 75th logomark repository for staff? Or just MarCom? - TM

- Communications plan (social, blog posts, eblasts, newsletters, ColLABorate) – MF/SB/COMS | 75 stories over the year

- Basic messaging – DF/COMS?

JANUARY (by end of January?)

- Share timeline/plan with BOD Jan. 8 - DF

- “Soft” launch Monday Jan 26? (messaging and landing page done; 75th logomark updates)

- Create website landing page for more information (History overview; curated content from 50th anniversary book; links to 75th related blog posts, etc.) and homepage feature – GS/DF

- Eblast announcing anniversary and what to expect in 2026 – BM/DF

- Update assets with logomark:

  - Update social channel profile pics with 75th logomark – SB/TM

  - Add to staff email signatures; use logo?- BM

  - Update APHL PPT template and letterhead – BM/TM/KA

  - Email/newsletter headers (all or select?) with logomark; headers or footers? – KA/PB

  - eUpdate “feature” / sidebar - BR

  - Lab Matters and other publications – BR/MR

  - Conference materials – BM/TM

- Develop Annual Conference video plan – KA/DF

FEBRUARY

- Continue work on, and promotion of, content (Social, Lab Matters and Blog) – COMS

- Photos/stories from labs over 75 years: equipment and instrumentation, mouth pipetting, etc.  – COMS

- Make “welcome to APHL” homepage image (not feature) - TM

MARCH

- Publish spread 1 in spring issue of Lab Matters – GS/BR

LAB WEEK (April 19-25)

NPHW WEEK (April 6-12)

- Share messaging about the value of lab work and public health labs – COMS

ANNUAL CONFERENCE (May 4-7)

- Build 75th anniversary into branding and messaging, preconference and onsite – BM/TM

- Ideas:

  - History display? “Then” and “now” images / faces of the association – spotlight members/leaders

  - Build 75th anniversary into awards ceremony

  - Promote an APHL Spirit Day at the conference (wear teal or your favorite APHL gear!)

  - Special certificate of member labs that have been with APHL for 75 years; or on PPT slide

  - Film screening

  - Build into health and wellness activities at AC, e.g. coloring pages, crossword

  - Collective artwork – send states an outline of their state to create their own artwork and then bring them all together at the AC to form a complete map (Or “75”)

  - 75th session at the AC – trivia based?

  - Art contest at the AC or incorporate into PHLAM art contest

  - Special raffle gift(s)?

  - Include happy anniversary messages in welcome session video

  - Introduce plenary sessions with themed video shorts

  - anniversary trivia on screens

JUNE

- Publish spread 2 in summer issue of Lab Matters – GS/BR

SUMMER

- APHL Week virtual staff celebration/recognition

- Then and Now with tenured staff

SEPTEMBER

- Publish spread 3 in fall issue of Lab Matters – GS/BR

- PHLAM

  - Incorporate into PHLAM art contest

  - Incorporate into PHLAM appreciation posts

NOVEMBER

Year-end wrap up / history / thanks

DECEMBER

- Publish spread 4 in winter issue of Lab Matters – GS/BR

ANNUAL REPORT (Spring 2027)

Build 75th anniversary into the 2026 report – GS